## HebePG
Hebe Payment Gateway
To be completed by: |  |  | Hieu Nguyen
| Total modules |  | 9
| Total hours |  | 22
| Cost per hour |  | 10
| Total cost |  | 220
Deadline: |  |  | 2018-01-10
Implement HebePaymentGateway(HebePG)
% done | Phase | Hour(s) | Due By | Notes
Implement HebeGateway
0% | Project Initiation | 2 | 2018-01-06 | Initiate project source code.
0% | Implement Handshake endpoint | 1 | 2018-01-06 | An endpoint that hebe site can initiate payment or set up connection between the two systems.
0% | Implement payment options UI | 2 | 2018-01-06 | a page that show a list of options such as: - Thanh toan bằng ví NL - Thanh toán băng ATM nội đia - Thanh toán băng credit card
0% | Implement pay with NganLuong. | 3 | 2018-01-07 | Proceed the selected payment option by user.
0% | Implement cancel to pay. | 2 | 2018-01-07 | Cancel payment and go back to hebe site
0% | Implement payment result handler | 3 | 2018-01-07 | An endpoint that NganLuong will call once payment is done(success, fail or cancel)
0% | Integrate HebePG to Arcardier
0% | Publish HebePG | 3 | 2018-01-08 | Assume that domain and host is ready. We will deploy HebePG to host and make it available on internet.
0% | Configuration HebePG on Arcardier | 2 | 2018-01-09 | Setup admin > Payment > add custom Payment method. Set up page Thanh toan to show Payment method as expected.
0% | Test payment on arcardier hebe and fix bugs | 4 | 2018-01-10